## Project Information
PROJECT BASIC INFORMATION
Project Name | Huntd
Name of Product | The best app for hiring web3 developers.
| Links | Test plan | Permission table | RTM Mobile, RTM Website
|  | Jira | TestRail WEB | TestRail Mobile
Product Description | Huntd is a comprehensive job search and application tracking app designed to assist job seekers in their quest for employment. With its user-friendly interface and powerful features, this app is essential for individuals actively seeking job opportunities.
Project Description | Mission of the project | Conduct testing to verify the quality of the web and mobile application.
Ensure the application is released without defects.
| Project output product | Test Summary report and Defects evaluation
| Project Type | Testing
Project Duration | Start date | 2024-12-06 | End date | 2024-12-10
Test Objectives | The test objectives are the functionality of the web version and mobile version of the “Huntd”. The project focuses on the possibility to interact with the main objects of the website and app.
For Website the main objectives are user registration, job searching and applying, chats and profile info
For Mobile App the main objectives are user registration, chats and user profiles ettings

## Test Summary
Execution Rate for Huntd Web app | [6 empty] | Execution Rate for Huntd mobile app
Executed test cases |  | 67 | 100% |  |  |  | Executed test cases |  | 27 | 100%
Passed |  | 60 | 89.55% |  |  |  | Passed |  | 21 | 77.78%
Failed |  | 9 | 13.43% |  |  |  | Failed |  | 6 | 22.22%
Huntd Web bugs by Priority
Critical |  | 14 | 18.67%
High |  | 19 | 25.33%
Medium |  | 26 | 34.67%
Low |  | 16 | 21.33%
Web features | [6 empty] | Mobile features
No. | Features | Tests | Passed |  | Failed |  | No. | Features | Tests | Passed |  | Failed
1 |  | 20 | 15 | 75% | 5 | 25% | 1 |  |  |  | #DIV/0! |  | #DIV/0!
2 |  | 20 | 10 | 50% | 10 | 50% | 2 |  |  |  | #DIV/0! |  | #DIV/0!
3 |  | 20 | 19 | 95% | 1 | 5% | 3 |  |  |  | #DIV/0! |  | #DIV/0!
4 |  | 20 | 9 | 45% | 11 | 55% | 4 |  |  |  | #DIV/0! |  | #DIV/0!
5 |  | 20 | 12 | 60% | 8 | 40% | 5 |  |  |  | #DIV/0! |  | #DIV/0!
6 |  | 10 | 9 | 90% | 1 | 10% | 6 |  |  |  | #DIV/0! |  | #DIV/0!
7 |  | 20 | 6 | 30% | 14 | 70% | 7 |  |  |  | #DIV/0! |  | #DIV/0!
8 |  | 20 | 20 | 100% | 0 | 0% | 8 |  |  |  | #DIV/0! |  | #DIV/0!
| Latest (Coverage) | 150 | 100 | 66.67% | 50 | 33.33% |  | Latest (Coverage) | 0 | 0 | #DIV/0! | 0 | #DIV/0!